## Test Plan
Detailed Test Plan
Test Case | Test Case Description | Step | EC Screen | Description | Data | Expected Results | Pass or Fail | Comments
1 | Rule Group - Basic Actions | 1 | Rule Groups | Create a new Rule Group | Report Only unchecked | Rule Group created; date sources required | Pass
|  | 2 | Rule Groups | Update a Rule Group |  | Rule Group updated; Journal Entry Created | Pass
|  | 3 | Rule Groups | Delete a Rule Group |  | Rule Group deleted; Journal Entry Created | Pass
|  | 4 | Rule Groups | Create a report only Rule Group | Report Only checked | Rule Group Created; Date Sources set to NULL | Pass
|  | 5 | Rule Groups | Attempt to add a duplicate Rule Group Code |  | Error - Rule Group not added | Pass
|  | 6 | Rule Groups | Attempt to change a Rule Group Code to a Duplicate Value |  | Error - Rule Group not changed | Pass
|  | 7 | Rule Groups | Enter an invalid Date source for a non report-only Rule Group |  | Error - invalid date source | Pass
2 | Rule - Basic Actions | 1 | Rules | Create a new Rule |  | Rule created; Descr, Cat/Sub, and SQL reqd | Pass
|  | 2 | Rules | Update a Rule |  | Rule updated; Journal Entry Created | Pass
|  | 3 | Rules | Delete a Rule |  | Rule deleted; Journal Entry Created | Pass
|  | 4 | Rules | Default the object id source by leaving element blank |  | defaults to OBJECT_ID | Pass
|  | 5 | Rules | Enter an override value for object_id source (not object_id) |  | override value saved and used in generated SQL | Pass
|  | 6 | Rules | Default the daytime source by leaving element blank |  | defaults to DAYTIME | Pass
|  | 7 | Rules | Enter an override value for daytime source (not daytime) |  | override value saved and used in generated SQL | Pass
|  | 8 | Rules | Default the alternate unique key source by leaving element blank |  | defaults to NULL | Pass
|  | 9 | Rules | Enter an override value for alternate unique key source (not NULL) |  | override value saved and used in generated SQL | Pass
|  | 10 | Rules | Populate Addnl info with mix of variables and constants | preface variables with a colon ':' | data element built correctly in the generated SQL section | Pass
|  | 11 | Rules | Activate a Rule with valid SQL |  | Rule saved, generated SQL shown correctly | Pass
|  | 12 | Rules | Attempt to activate a Rule with invalid SQL |  | Error - invalid dynamic SQL | Pass
|  | 13 | Rules | Enter FROM SQL using :START_DATE and :END_DATE variables | Not usually used | Generated SQL will replace FROM DATE and TO_DATE with sysdate | Pass
|  | 14 | Rules | Enter misc Rule attributes (Rule Category, Target Attribute, Object Type, Rule Description, Comments, Role) |  | Attribute values stored for Rule | Pass
|  | 15 | Rules | Insert/Update Rule when there is a default Logging Level Set | CT_DQ_LOGGING_LEVEL | Default logging level populated | Pass
|  | 16 | Rules | Insert/Update Rule when there is a no default Logging Level Set |  | Logging level left NULL | Pass
|  | 17 | Rules | Insert/Update Rule when there is are multiple default Logging Levels Set |  | Logging level left NULL | Pass
|  | 18 | Rules | Browse for Rules Using the Subcategory |  | Rules assigned to the category and subcategory are returned | Pass
|  | 19 | Rules | Browse for Rules Using the Category | leave subcategory NULL | Rules assigned to the category are returned | Pass
|  | 20 | Rules | Browse for Rules w/ nothing populated in Navigator | leave category and subcategory NULL | All Rules returned (even those w/ no Cat and/or subcat populated) | Pass
3 | Rule to Group Combinations | 1 | Rules | Associate a Rule to a Rule Group |  | Rule to Rule Group record created | Pass
|  | 2 | Rules | Delete a Rule to Rule Group Association |  | Record deleted; journal entry created | Pass
|  | 3 | Rules | Associate a Rule with multiple Rule Groups |  |  | Pass
|  | 4 | Rule Groups | Select a Rule Group with multiple Rules |  | Rules displayed for Group | Pass
4 | Run Rules - Basic Actions | 1 | Run Rules | Run Rule Group |  | All rules for the Rule Group are executed; from and end dates are generated from Rule Group set-up and records limited to those dates; counts and logs shown | Pass
|  | 2 | Rule Run Logs | Browse for a specific Rule |  | Group Run displayed with parameters (group id) | Pass
|  | 3 | Run Rules | Run Rule Group for a single Rule |  | A Rule level run is executed; counts and logs shown | Pass
|  | 4 | Rule Run Logs | Browse for a specific Rule |  | Rule Run displayed with parameters (group and rule) | Pass
|  | 5 | Run Rules | Browse history of Runs by Group | Change Run Log Date back to include multiple Runs | All Runs >= the entered Run Log Date are displayed for the entered Group | Pass
|  | 6 | Run Rules | Browse history of Runs by Group and Rule |  | All Runs >= the entered Run Log Date are displayed for the entered Group and Rule (runs for different Rule level runs would be omitted). The detail section will only show the information for the entered navigator Rule | Pass
5 | Rule Results - Basic Actions | 1 | Rule Results | Browse Rule Results using hierarchy and date range |  | All Rule Results for the data range and hierarchy are displayed | Pass
|  | 2 | Rule Results | Alter the navigator dates to change the number of returned Rule Results |  | Rule Results filtered by entered date range | Pass
|  | 3 | Rule Results | Alter the hierarchy to change the number of returned Rule Results |  | Rule Results filtered by entered hierarchy | Pass
|  | 4 | Rule Results | Rerun an individual Rule Result | Highlight row and click Run Selected button | Only selected record is rerun - as indicated by the last run date (no other Rule Results should have been rerun) | Pass
|  | 5 | Rule Run Logs | Browse for a specific Rule |  | Error Run displayed with parameters (Rule, Object ID, daytime, alt unique key) | Pass
|  | 6 | Rule Results | Rerun all displayed Rule Results | Click Run All button | Only the displayed Rule Results are rerun - as indicated by the last run date (no other Rule Results should have been rerun) | Pass
|  | 7 | Rule Run Logs | Browse for a specific Rule |  | Error Hierarchy Run displayed with parameters (Rule, Hierarchy object, date range) | Pass
6 | Default Navigator Values | 1 | Maintain User Settings | Set up Group Model Type for 'Facility' to operational |  |  | Pass
|  | 2 | Maintain User Settings | Set up Navigator defaults for 'Default Facility' w/ operational hierarchy values |  |  | Pass
|  | 3 | Rule Results | Go to Rule Results screen to confirm defaulting |  | Default group type used and Navigator values populated | Pass
|  | 4 | Maintain User Settings | Set up Group Model Type for 'Facility' to collection_point |  |  | Pass
|  | 5 | Maintain User Settings | Set up Navigator defaults for 'Default Facility' w/ collection point hierarchy values |  |  | Pass
|  | 6 | Rule Results | Go to Rule Results screen to confirm defaulting |  | Default group type used and Navigator values populated | Pass
7 | Error Correction | 1 | Run Rules | Run a Rule Group/Rule which generates Rule Results | Generate > 4 errors | Rule Results generated | Pass
|  | 2 | Rule Results | Browse Rule Results |  | Rule Results displayed | Pass
|  | 3 | EC Txn | Correct several of the displayed Rule Results | Correct at least 4 errors | EC Data updated | Pass
|  | 4 | Rule Results | Rerun the Rule Results by Run Selected button |  | Rule Results dropped from view; old Rule Results logged on journal table; Resolved Count reflected (via SQL) | Pass
|  | 5 | Rule Results | Rerun the Rule Results by Run All button | Show at least 2 errors | Rule Results dropped from view; old Rule Results logged on journal table; Resolved Count reflected (via SQL) | Pass
|  | 6 | Run Rules | Rerun the Rule Group/Rule | Have at least 1 error that has been corrected but not rerun (i.e. still shows up on Rule Results) | Log counts reflect corrections (lower errors and resolved count) | Pass
|  | 7 | Rule Results | Browse for the Rule Results |  | Corrected Rule Results no longer appear on the counts, or as Rule Results; | Pass
8 | Rule Result Retention | 1 | Run Rules | Run a Rule Group/Rule which generates Rule Results |  | Rule Results are created | Pass
|  | 2 | Rules | Set one of the Rules from step #1 to have a Rule Result Retention value = 0 |  | Retention Days is saved | Pass
|  | 3 | Rules | Associate the Rule with another Rule Group - which has a more limited date range than the Rule Group from step #1 | YTD to MTD | Rule Group Combo saved | Pass
|  | 4 | Run Rules | Run the Rule Group from Step #3 |  | Rule Results generated for the new data range; all other Rule results are removed/deleted (logged on journal table); Rolled Off Counts reflected | Pass
|  | 5 | Rule Results | Browse for Rule Results |  | Only the Rule Results for the restricted date range exist | Pass
|  | 6 | Rules | Change the Rule Result Retention value to 5 (days) |  | Retention Days is saved | Pass
|  | 4 | SQL | Update the last run date on a set of the Rule Results to be older than sysdate - Retention days |  | Rule Results updated | Pass
|  | 5 | Run Rules | Rerun the Rule Group/Rule | must update records which will not be reidentified in rule run | Rule Results older than retentition days (and which have not been re-identified) have been deleted; logged on journal table; Rolled Off Counts reflected | Pass
9 | Rule Logging Levels | 1 | Rules | Define a Rule with a blank Logging Level | No EC Code should be marked as default | Rule saved without Logging Level populated | Pass
|  | 2 | Run Rules | Run Rule Group for time with rule results |  | Rule Logging should be at Rule level | Pass
|  | 3 | Rules | Define a Rule (different that Rule in Step #1) with a Rule Logging Level |  | Logging Level saved on Rule | Pass
|  | 4 | Run Rules | Run Rule/Group from Step 3 |  | Rule Logging should be at Rule level | Pass
|  | 5 | Rule Run Logs | Browse for Rule Runs |  | Detailed logging level should be blank | Pass
|  | 6 | Rules | Define a Rule (different that Rule in Step #1,#3) with a Logging Level of a hierarchy level |  |  | Pass
|  | 7 | Run Rules | Run Rule/Group from Step 5 |  | Rule Logging should be at appropriate hierarchy level | Pass
|  | 8 | Rule Run Logs | Browse for Rule Runs |  | Detailed logging level should be populated at correct hierarchy level | Pass
|  | 9 | Rule | Configure a Rule with detailed logging, but where no Rule Results will be generated |  |  | Pass
|  | 10 | Run Rules | Run Rule |  |  | Pass
|  | 11 | Rule Run Logs | Browse for Rule Runs |  | Only a single summary log created at a Rule level with all zero counts | Pass
10 | Screen Security | 1 | User Maintenace | Choose/create a user with the default access | Should not be linked to any DQ roles |  | Pass
|  | 2 | EC | Log on to EC with user |  | No DQ Screens appear in tree | Pass
|  | 3 | Role Maintenance | Link user to DQ Role granting read only to DQ screens |  |  | Pass
|  | 4 | EC | Log on to EC with user |  | DQ Screens appear in tree | Pass
|  | 5 | Rule Groups | Browse Rule Groups |  | Rule Groups are shown; all read only | Pass
|  | 6 | Rules | Go to Rules Screen; enter Rule Category and Subcategory | Browse Rules | Rules are shown; all read only | Pass
|  | 7 | Run Rules | Go to Run Rules Screen | Browse Runs | Rule Runs are displayed; No access to click Run Rules button | Pass
|  | 8 | Rule Results | Go to Rule Results Screen and locate Rule Results | Browse Rule Results | Rule Results are displayed; No access either Run buttons | Pass
|  | 9 | User Maintenace | Switch to a user with access to maintain EC Rules |  |  | Pass
|  | 10 | Rules | Attempt to add/modify/delete Rules |  | User should have access to maintain Rules | Pass
|  | 11 | Rules | Attempt to add/modify/delete Rule Group Associations |  | User should have access to maintain Rule Group Combos | Pass
|  | 12 | User Maintenace | Switch to a user with access to maintain EC Rule Groups |  |  | Pass
|  | 13 | Rule Groups | Attempt to add/modify/delete Rule Groups |  | User should have access to maintain Rule Groups | Pass
|  | 14 | User Maintenace | Switch to a user with access to maintain EC Run Rules |  |  | Pass
|  | 15 | Run Rules | Attempt to run rule group |  | User should have access to run Rule Groups | Pass
|  | 16 | User Maintenace | Switch to a user with access to maintain EC Rule Results |  |  | Pass
|  | 17 | Rule Results | Attempt to rerun rule results |  | User should have access to rerun selected and rerun all rule results | Pass
11 | Object Partitioning | 1 | User Maintenace | Choose/create a user with object partitioning established |  |  | Pass
|  | 2 | Rule Results | Go to Rule Result and choose navigator values |  | Navigator values should be limited to object partition rules | Pass
12 | Rule Roles | 1 | Rule Results | Locate/generate Rule Results | Ideally results for multiple rules would be located | Rule Results displayed | Pass
|  | 2 | Role Maintenance | Create a new role | No need to assign any objects | Role Created | Pass
|  | 3 | User Maintenance | Link User to new role |  | Role Added to User | Pass
|  | 4 | Rules | For one of the Rules from step #1, assign the Rule to the new role |  | Rule linked to Role | Pass
|  | 5 | Rule Results | Locate/generate Rule Results |  | Rule Results shows (same as in step 1) | Pass
|  | 6 | User Maintenance | Remove the role from the user |  | Role Removed | Pass
|  | 7 | Rule Results | Locate/generate Rule Results |  | Rule Results for Rule ID no longer visible | Pass
13 | SQL Flex Fields | 1 | CONFIG | Map one of the SQL Flex source fields on CT_DQ_RULE | Add Mapping; Regen Class | EC Class updated | Pass
|  | 2 | CONFIG | Map the corresponding SQL Flex field on CT_DQ_RULE_RESULTS | Add Mapping; Regen Class | EC Class updated | Pass
|  | 3 | Rules | Configure Rule using new SQL Flex field by populating source | e.g. last_updated_by |  | Pass
|  | 4 | Run Rules | Run Rule Group/Rule |  | Rule Results generated | Pass
|  | 5 | Rule Results | Browse Rule Results |  | New SQL Flex field appears and is populated on Rule Results | Pass
14 | Flex Fields | 1 | CONFIG | Map one of the Flex fields on CT_DQ_RULE | Add Mapping; Regen Class | EC Class updated | Pass
|  | 2 | Rules | Go to Rule screen |  | New flex field visibile and can be populated | Pass
|  | 3 | CONFIG | Map one of the Flex fields on CT_DQ_RULE_GROUP | Add Mapping; Regen Class | EC Class updated | Pass
|  | 4 | Rule Groups | Go to Rule Group screen |  | New flex field visibile and can be populated | Pass
15 | Launching Business Functions | 1 | Rules | Associate a Rule with the appropriate EC Screen |  |  | Pass
|  | 2 | Run Rules | If not already done, run Rule Group for setting which will return Rule Results |  |  | Pass
|  | 3 | Rule Results | Retrieve the Rule Results and Press the Go to BF button |  | New EC screen opened for appropriate EC screen. In 9.3, the hierarchy and object will not be automatically passed to the EC screen | Pass
|  | 4 | User Maintenance | Identify a user who has access to the Rule Results bf, but does not have access to the associated EC screen |  |  | Pass
|  | 5 | Rule Results | Retrieve the Rule Results and Press the Go to BF button |  | Launching EC screen indicates an access issue | Pass
|  | 6 | Rule Results | Retrieve Rule Results for a Rule not associated with an EC screen; click the go to BF button |  | Blank EC screen launched with message abt no BF configured | Pass
16 | Performance Limits | 1 | Attributes | Set the maximum results to a value less than the expected encountered rule results |  |  | Pass
|  | 2 | Run Rule | Run Rule Group |  | Rule run stopped at rule which exceeds maximum result configuration with a Failure | Pass
|  | 3 | Attributes | Set the maximum time to a value less than the expected encountered rule run time |  |  | Pass
|  | 4 | Run Rule | Run Rule Group |  | Rule run stopped at rule which exceeds maximum time configuration with a Failure | Pass
|  | 5 | Attributes | Set the maximum number of rule results to a number les than existing rule results |  |  | Pass
|  | 6 | Rule Results | Browse rule results where there are more results than configured max |  | Only the configured number of max rule results returned in detail section | Pass
17 | Single Sign-on | 1 | EC | Log on to EC using single sign on |  | Log on successful | Pass
|  | 2 | EC | Log on to EC using id/password |  | Log on successful | Pass
18 | EC Schedules | 1 | EC Schedules | Create an EC Schedule with the RunDQRules business action, and schedule a Rule Group |  | Rule Group Run Successfully | Pass
|  | 2 | Run Rules | Browse Run Rules |  | Rule Group Run Displayed | Pass
|  | 3 | EC Schedules | Create an EC Schedule with the RunDQRules business action, and schedule a Rule Group & Rule |  | Rule Group/Rule Run Successfully | Pass
|  | 4 | Run Rules | Browse Run Rules |  | Rule Run Displayed | Pass
|  | 5 | EC Schedules | Create an EC Schedule with the RunDQRules business action, and schedule a Rule Group & Rule |  | Rule Group Run Successfully | Pass
|  | 6 | Run Rules | Browse Run Rules |  | Rule Run Displayed; override parameters shown on run (and used by run) | Pass
|  | 7 | EC Schedules | Run an EC schedule with an invaild Rule Group code |  | Job fails with Rule group Error | Pass
|  | 8 | EC Schedules | Run an EC schedule with an invaild Rule |  | Job runs, but no rules processed | Pass